## Sheet1
Week | Backend
2022-04-04 | CI pipeline
2022-04-11 | CD pipeline
2022-04-18 | Prediction API with empty data
2022-04-25 | Prediction data
2022-05-02 | Prediction API with data
2022-05-09 | Unit test
2022-05-16 | Build application image
2022-05-23 | Kubernetes deployment
2022-05-30 | Monitoring setup
2022-06-06 | Ready for QA
2022-06-13 | Fix bugs detected by QA
2022-06-20 | Go live
Goals
ML API
CICD pipelines
Containerization